# Orfeu US Market Entry — Research Plan

Lean DIY Version  ·  4 Research Streams  ·  Strategist — Jun 2026

Reference: Heart+Mind Strategies proposal (May 20, 2026)

Context & Design Principle

The Heart+Mind Strategies proposal outlines a rigorous full-service research program at ~$377K USD. It is well-designed but built for a client that delegates the entire process to an agency. This plan takes the same strategic questions and builds a lean, hands-on version that Felipe can execute directly — with AI support, Orfeu's own data assets, and targeted fieldwork focused on South Florida as the beachhead market. Total estimated cost: $3,000–$8,000 USD vs. $377K — roughly 50× cheaper.

| H&M Phase | H&M Budget | This Plan Equivalent | DIY Cost |
| --- | --- | --- | --- |
| Phase 1: Discovery + Framing (secondary data) | $29,505 | Stream 3: Category analytics (AI + free/paid sources) | $300–$800 |
| Phase 2: Consumer journey / wet sampling | $101,640 | Stream 2: FL consumer + influencer interviews + sampling | On hold |
| Phase 2: Trade interviews (20 IDIs) | $44,205 | Stream 1: Retailer / Distributor / Broker interviews | $0–$500 |
| Phase 3: National quantitative survey (n=2,000) | $112,560 | Deprioritized — Board brief doesn't require quant at this stage | — |
| Phase 4: Financial feasibility / P&L | $68,500 | Felipe + Alquemia (in scope of Orfeu project) | — |
| Phase 5: Strategy + Board Brief | $21,105 | Synthesis and PPT — Felipe + AI | $0 |
| Brand Cases (not in H&M scope) | — | Stream 4: Specialty coffee brand cases | $0 |
| TOTAL | ~$377K | TOTAL ESTIMATED | $3,000–$8,000 |

Stream 1 — Trade Interviews: Retailers, Distributors & Brokers

Executed by: Felipe directly  ·  Cost: ~$0–$500 (travel + tools)  ·  Timeline: 4–6 weeks

## Objective

Understand the real gatekeeping dynamics of US specialty coffee distribution. Map how premium CPG coffee brands get shelf space, who the decision-makers are at the distribution layer, what commercial terms look like, and where Orfeu fits (or needs to be adapted) in the value chain. KeHE is already a known lead — this stream validates and expands that.

## Target Profiles — 15–20 interviews, 45–60 min each

| Profile | Target N | Key Questions | How to Reach |
| --- | --- | --- | --- |
| Specialty grocery buyers (Whole Foods, Fresh Market, Sprouts, Earth Fare) | 2-3 | How do you evaluate new specialty coffee brands? What does Orfeu need to show to get on shelf? Category trends. | LinkedIn outreach; intro via KeHE relationship; Orfeu US contacts |
| National / regional distributors (KeHE, UNFI, regional specialty) | 2-3 | Onboarding requirements, margin expectations, velocity benchmarks, category shelf dynamics, what kills a new brand. | KeHE contact (already warm); UNFI via LinkedIn; SCA distributor directory |
| Specialty coffee brokers / sales reps (independent, work with multiple brands) | 2-3 | How do they choose brands to represent? Commission structure, territory model, what makes a pitch compelling. | SCA directory, LinkedIn, referrals from distributor contacts |
| On-premise / foodservice buyers (hotels, restaurants, specialty cafés) | 3–4 | B2B entry point for premium brands. How do they discover Brazilian specialty? Willingness to pay premium. | LinkedIn; direct outreach to F&B directors at boutique hotels in Miami/NYC |
| Coffee importers / roasters who work with Brazilian origin | 2–3 | Import logistics, certification requirements, what US buyers actually want from Brazil origin. | SCA importer list; Specialty Coffee Importers Association; LinkedIn |

## Protocol

- Discussion guide: 10–12 questions, semi-structured. Felipe leads — conversational, not formal.

- Record all calls (Otter.ai or Riverside.fm — both ~$15/month). AI auto-transcription.

- After each call: 10-min debrief note in standard template (Claude assists with synthesis).

- After all interviews: cross-interview theme analysis using AI — patterns in language, barriers, opportunities.

- Do NOT send advance questionnaire. Keep it conversational — these are trade professionals who respond to peers, not survey forms.

## Key Outputs

- Trade channel map: who controls what, what the path to shelf looks like for a brand like Orfeu

- Commercial reality check: margins, velocity benchmarks, listing fees, co-op requirements

- Gatekeeping narrative: what story and proof points resonate with each trade layer

- KeHE scenario validation: is KeHE the right first distributor, or are there better fits?

- Priority channel recommendation (retail / foodservice / DTC / all-of-the-above)

## Tools & Cost

| Tool | Purpose | Cost |
| --- | --- | --- |
| Otter.ai or Riverside.fm | Call recording + auto-transcription | ~$15/month |
| Claude / ChatGPT | Cross-interview synthesis + theme extraction | Existing subscription |
| LinkedIn Sales Navigator (1 month) | Finding and outreaching trade contacts | ~$99/month |
| Google Docs / Notion | Interview notes + synthesis template | Free |
| Travel (if needed) | In-person meetings in FL or trade shows | $300–$500 |

Stream 2 — Consumer & Influencer: Sampling + Qualitative (Florida)

Executed by: Felipe + local support  ·  Cost: ~$2,500–$4,500  ·  Timeline: 4–5 weeks

## Why Florida

- Largest Brazilian diaspora in the US (300K+ in South Florida alone) — built-in brand familiarity pool

- Mature specialty coffee culture: Miami has a thriving independent café scene

- Premium consumer base willing to pay for specialty and origin stories

- Manageable geography for focused fieldwork — Miami + Ft. Lauderdale

- Proximity to KeHE's Southeast distribution footprint

- Orfeu already has some existing contacts/interest from the FL market

## Component A — Wet Sampling Sessions (2–3 sessions, Miami)

The most irreplaceable insight: how do US consumers taste, react to, and talk about Orfeu when they have it in their hands. H&M budgeted $75K for this — we replicate the core version for under $2K.

| Element | DIY Approach | Detail |
| --- | --- | --- |
| Format | 3 sessions × 6–8 participants = 18–24 consumers total | 90 minutes per session. Informal, tasting + conversation, not a "focus group." |
| Venue | Partner with a specialty coffee shop or co-working space in Miami (Wynwood / Brickell / Coral Gables) | Ask for the space off-hours (morning or evening) in exchange for a small fee or future partnership mention. $0–$200 per venue. |
| Recruitment | Combination of: (1) Brazilian diaspora community groups (WhatsApp, Facebook), (2) Specialty coffee enthusiast groups (Meetup, IG), (3) Screener via Typeform distributed on local channels | Target: 50% specialty coffee purchasers, 30% premium grocery shoppers, 20% Brazilian diaspora. Age 28–55. |
| Incentive | $30–$40 Amazon gift card or Venmo per participant | Total: ~$600–$720 for all sessions |
| Tasting protocol | 5–6 Orfeu SKUs tasted blind then revealed. Include 1–2 competitor benchmarks (e.g., Illy, Lavazza, Stumptown) | Blind first, then branded reveal — captures pure taste reaction vs. brand influence |
| Discussion guide | 15–20 questions: first impression, taste language, origin story reaction, pricing perception, purchase intent, channels | Felipe facilitates. Record on phone (Otter.ai). One note-taker. |
| Brand attribute sorting | 10–12 attribute cards: "artisanal," "Brazilian," "luxury," "sustainable," "award-winning," etc. | Participants sort by "describes Orfeu" / "doesn't describe" / "could describe." Maps brand perception gaps. |

## Component B — Online Async Video Qual (15–20 consumers)

Extends geographic and demographic reach beyond the in-person sessions without the cost of a second market. Respondents answer 4–6 open-ended video questions at home with product samples shipped in advance.

| Element | Approach | Cost |
| --- | --- | --- |
| Platform | Respondent.io or UserInterviews.com for recruitment + async video | $50–$80 per recruited participant. Budget for 15–20 = ~$1,000–$1,600 |
| Sample kit | Ship 2–3 Orfeu products (ground + whole bean + sachets) + simple prep guide | ~$15–$20 per kit including shipping = $225–$400 total |
| Questions | Video prompts: unbox reaction, brewing experience, taste description, origin story reaction, price point perception, who they'd give it to | Felipe reviews videos. AI transcribes + summarizes patterns. |
| Profile | Specialty coffee buyers outside FL: NYC, Chicago, LA, Austin — to see if FL generalizes | Broadens basis for Board recommendation without a full multi-market fieldwork program |

## Component C — Influencer Interviews (8–12 people)

| Profile | Target | Method | Key Questions |
| --- | --- | --- | --- |
| Specialty coffee influencers (IG/TikTok/YouTube, 10K–200K followers) | 4–5 | 30-min video call + Orfeu sample kit sent in advance | What does "origin" mean in specialty coffee today? How do they talk about Brazil? What would make them feature Orfeu? |
| Lifestyle / sustainability influencers (food, travel, premium lifestyle, FL-based) | 3–4 | 30-min video call + sample kit | How do they discover premium CPG? What brand stories resonate with their audience? Content fit assessment. |
| Brazilian-American creators (diaspora community, FL-based) | 2–3 | DM + 20-min call | How do they engage with Brazilian brands? What would make Orfeu resonate with the diaspora community? |

Finding influencers: Instagram search #specialtycoffee #miamicoffee + SparkToro (free tier) to map which accounts have relevant audiences. No paid partnerships needed at this stage — this is research, not activation.

## Key Outputs

- Taste and sensory language map: how US consumers describe Orfeu in their own words

- Brand attribute priority: which attributes land (origin, awards, sustainability, luxury, Brazil) and which don't

- Positioning hypothesis validation: does the "Oscar of Coffee" narrative work for US consumers?

- Sachet / format reaction: does the sachet format excite or confuse US buyers?

- Price point comfort zone: what does a fair price feel like for the product experience?

- Influencer fit map: who would naturally carry the Orfeu story

- Florida-specific entry hypothesis for Board recommendation

## Budget Summary — Stream 2

| Item | Est. Cost |
| --- | --- |
| Venue (3 sessions × ~$100) | $0–$300 |
| Participant incentives (24 in-person × $35) | ~$840 |
| Online qual recruitment (15 × $70 avg) | ~$1,050 |
| Sample kits — in-person + online (35 total) | ~$600–$700 |
| Shipping (online kits) | ~$200–$300 |
| Otter.ai / transcription | ~$30 (2 months) |
| SparkToro (influencer mapping, 1 month) | ~$50 |
| Contingency / incidentals | $200–$300 |
| TOTAL | $2,970–$4,570 |

Stream 3 — Category Secondary Data & Analytics

Executed by: Felipe + AI (Claude/GPT)  ·  Cost: ~$300–$1,500  ·  Timeline: 2–3 weeks parallel

## Objective

| Source | Content | Access | Est. Cost |
| --- | --- | --- | --- |
| NCA — National Coffee Association nca.org | Annual "National Coffee Data Trends" report. US consumption data, brewing methods, purchasing behavior by segment. | Free summary available. Full report with NCA membership or direct purchase. | $0–$295 (NCA membership) |
| SCA — Specialty Coffee Association sca.coffee | Specialty coffee market data, origin trends, US import statistics, consumer research briefs. | SCA Producer Membership (~$295/yr) unlocks research library. | $0–$295 (SCA membership) |
| USDA Foreign Agricultural Service fas.usda.gov | US coffee import/export data by origin country, volume and value. Brazil vs. Colombia vs. other origins. | 100% free, public data. | $0 |
| ICO — International Coffee Organization ico.org | Global production, trade flows, origin pricing data. Brazil positioning globally. | Free public reports. Full data with membership. | $0 |
| Amazon Seller Central (Orfeu's own data) | Orfeu's existing Amazon US sales: search terms, conversion rates, reviews, Buy Box performance, competitor asin analysis. | Already available to Orfeu — just needs to be extracted and analyzed. | $0 (already owned) |
| Amazon Reviews Mining (competitors) Compe: Illy, Lavazza, Stumptown, Intelligentsia, Death Wish | Scrape top 200–500 reviews per competitor brand using free tools. Analyze language, complaints, what consumers love. | ReviewMeta.com (free), Helium 10 free tier, or simple Python scrape. | $0–$97 (Helium 10 1 month) |
| Google Trends | Search volume trends: "Brazilian coffee", "specialty coffee", "single origin coffee" by US region. Free geo-filters for FL. | 100% free. | $0 |
| Jungle Scout / Helium 10 (1 month) helium10.com | Amazon BSR tracking, keyword search volume, competitor revenue estimates for coffee category. | One-month subscription for the research phase. | $39–$97 (cancel after) |
| Reddit — r/Coffee, r/espresso, r/coffee | Organic consumer language about Brazilian coffee, Orfeu mentions, specialty vs. supermarket debates. | Free. Search "Orfeu" + "Brazilian coffee" + "specialty coffee FL" etc. | $0 |
| Social listening — Instagram + TikTok | Hashtag analysis: #brasileiroscoffee, #specialtycoffee, #orfeu. Qualitative trend signals. | Free manual search. Brand24 or Mention free trials if needed. | $0–$50 |
| Euromonitor Passport passport.euromonitor.com | Packaged food & beverage market data for US coffee. Volume and value by segment. | Individual reports $1,500–$3,000. Check if Orfeu's team or a university library has access. | $0 if via library or partner; $1,500 if purchased |
| Mintel mintel.com | Consumer trends and CPG market reports. Coffee-specific reports with consumer attitudinal data. | Check if Orfeu has access. Summaries free. Full reports: $3,000+. Deprioritize unless available. | $0 if accessible; otherwise skip |

Build the category foundation that contextualizes the primary research. Understand market size, growth vectors, competitive positioning, consumer trends, and the distribution/channel landscape — using sources that are largely free or low-cost. AI dramatically accelerates synthesis of what would otherwise take weeks of analyst time.Data Sources by Category

## AI-Assisted Analysis Protocol

- Amazon reviews mining: extract top 500 reviews for Illy, Lavazza, Stumptown, Death Wish, Intelligentsia → Claude analyzes recurring themes, consumer language, unmet needs

- Orfeu Amazon data: paste Seller Central export → Claude identifies top search terms, conversion funnel gaps, review sentiment patterns

- Market reports synthesis: upload NCA / SCA / USDA PDFs → Claude extracts relevant data points, builds comparison tables

- Google Trends data: export CSV → Claude identifies regional opportunities, seasonality, trend trajectory vs. competitors

- Social listening: paste 50–100 relevant posts/comments → Claude identifies consumer language map and key perception themes

- Competitive pricing audit: manual scan of 10–15 competitor SKUs on Amazon + Whole Foods + Instacart → price ladder map by channel and format

## Key Outputs

- Category landscape brief: US specialty coffee market size, growth, key segments and channels (5–7 pages)

- Competitor positioning map: 8–10 brands plotted on price, origin, channel, and consumer positioning axes

- Amazon category intelligence: search term landscape, consumer language, Orfeu vs. competition performance

- Consumer trend signals: top themes from Reddit + social listening (organic, not prompted)

- Channel sizing: estimated volumes by channel (retail / foodservice / DTC / subscription) based on available data

- Florida market profile: demographics, specialty coffee penetration, Brazilian community size, relevant trade info

Stream 4 — Specialty Coffee Brand Cases

Executed by: Felipe + AI (Claude)  ·  Cost: ~$0  ·  Timeline: 1–2 weeks parallel

## Objective

Learn from brands that have navigated a similar challenge: entering the US as a premium specialty coffee brand, building origin credibility, and choosing the right channel mix. Some are direct competitors. Some are analogues from other premium food/beverage categories. All teach something specific about Orfeu's entry options. This is 100% desk research + AI synthesis — no fieldwork.

## Brand Case List — 8 Cases

| Brand | Origin | Relevance to Orfeu | Key Question to Answer |
| --- | --- | --- | --- |
| Illy | Italy → US | Most direct analog: premium European origin brand, full retail + foodservice + DTC. Already in US for 30+ years. | How did they establish premium positioning before Amazon existed? How do they manage B2C vs. B2B channel tension? |
| Lavazza | Italy → US | Mass-premium Italian brand. More accessible than Illy. Competing on "Italian coffee culture" not just quality. | How do you build origin recognition when the origin is less known than Italian in specialty coffee (Brazil vs. Italy)? |
| Nespresso | Switzerland → US (Nestlé) | Built a premium closed-system business. Strong DTC + flagship stores + B2B. Subscription model. | What can Orfeu learn about DTC premium subscription in the US? Capsule format opportunity? |
| Intelligentsia | US (Chicago) | Pioneered "third wave" specialty positioning in the US. Acquired by Peet's. High-end retail + café + B2B roaster. | How do you build trade credibility before consumer recognition? Role of barista community as tastemakers. |
| Blue Bottle Coffee | US (Oakland) → Japan → global | Premium DTC-first, then retail. Strong brand storytelling. Acquired by Nestlé $500M. | DTC + subscription model for premium specialty. How they priced and built a direct relationship vs. trade. |
| Stumptown Coffee | US (Portland) → National | Third wave pioneer. Strong café + wholesale + grocery. Acquired by JAB Holding (Peet's group). | Trade-first growth model: how building barista/roaster credibility translated to retail shelf. |
| Counter Culture Coffee | US (NC) | B2B-first specialty roaster. Training program as a market entry tool — cafés buy because of the education. | How the training/education model drives B2B penetration. Could Orfeu's "award-winning" story do the same? |
| Cafés do Brasil / Brazil Coffee Nation | Brazil → US | Brazilian origin brand attempts in the US. Some have failed, some are nascent. | What has NOT worked for Brazilian coffee brands in the US? What are the specific barriers for "Brazilianness" as an origin story? |

## Case Template — Consistent Structure for Each Brand

- 1. Brand origin and founding story (2–3 sentences)

- 2. US entry strategy: channel first chosen, geographic beachhead, when and how

- 3. Positioning and messaging: what story they told, to whom, in what language

- 4. Target consumer segment: who they were vs. who they became

- 5. Pricing strategy: price ladder, entry SKU, premium SKU

- 6. Trade vs. DTC balance: how they weighted the channels and why

- 7. Key inflection points: what worked, what failed, what they changed

- 8. Current state: market position, revenue scale, channel mix today

- 9. 3 specific lessons for Orfeu (explicit, not generic)

## Execution Method

- Claude + web research for each case: company websites, Crunchbase, trade press (Roast Magazine, Sprudge, Daily Coffee News), LinkedIn, press releases

- For each brand: 45–60 min of focused desk research + AI synthesis → fills the template above

- Total time: 1–2 days to complete all 8 cases

- Output format: one 2-page summary per brand + master comparison table (8 brands × 9 dimensions)

Master Research Plan — Timeline & Sequencing

| Week | Stream 1 Trade Interviews | Stream 2 Consumer / FL | Stream 3 Secondary Data | Stream 4 Brand Cases | Milestone |
| --- | --- | --- | --- | --- | --- |
| Wk 1 | Build target list (20 contacts) Start LinkedIn outreach | Recruit participants Book Miami venues Ship sample kits | Pull all free data sources Amazon Orfeu export Competitor review scrape | Start 4 brand cases (Illy, Lavazza, Intelligentsia, Blue Bottle) | Research Design locked |
| Wk 2 | First 5–6 interviews Refine discussion guide | Online qual running (async video responses) | NCA + SCA synthesis Google Trends analysis Reddit mining | Complete 4 more cases (Nespresso, Stumptown, Counter Culture, Brazil) | Brand Cases complete Secondary data 50% |
| Wk 3 | Interviews 7–12 Patterns emerging | Miami Session 1 Miami Session 2 | Competitor positioning map Amazon category intelligence complete | — (done) | Consumer fieldwork 50% Trade interviews 60% |
| Wk 4 | Interviews 13–18 Saturation check | Miami Session 3 Influencer interviews (8) | Final synthesis + FL market profile | — | All primary fieldwork complete |
| Wk 5 | Cross-interview synthesis (AI-assisted) | Consumer + influencer synthesis | Category landscape brief complete | — | All synthesis complete |
| Wk 6 | — | — | — | — | Integrated findings Board Brief draft Strategic implications |

Total Budget & Tool Stack

| Stream | Item | Est. Cost |
| --- | --- | --- |
| Stream 1 | LinkedIn Sales Navigator (1 month) | $99 |
| Stream 1 | Otter.ai / Riverside.fm (2 months) | $30 |
| Stream 1 | Travel (if needed for in-person meetings) | $0–$500 |
| Stream 2 | Participant incentives (in-person) | $840 |
| Stream 2 | Sample kits + shipping | $800–$1,000 |
| Stream 2 | Online qual recruitment (Respondent.io) | $1,000–$1,600 |
| Stream 2 | Venue (3 sessions) | $0–$300 |
| Stream 2 | SparkToro (1 month, influencer mapping) | $50 |
| Stream 3 | SCA membership (annual, unlocks research library) | $295 |
| Stream 3 | Helium 10 / Jungle Scout (1 month, Amazon intelligence) | $97 |
| Stream 3 | Euromonitor report (optional — deprioritize if cost is prohibitive) | $0 or $1,500 |
| Stream 4 | No direct cost — AI + desk research | $0 |
| All streams | Claude / AI tools (existing subscription) | $0 |
| All streams | Contingency / incidentals | $200 |
| TOTAL (without Euromonitor) |  | $3,411–$5,011 |
| TOTAL (with Euromonitor) |  | $4,911–$6,511 |

Outputs for August 2026 Board Brief

| Output | Source Streams | Format |
| --- | --- | --- |
| US specialty coffee category landscape (size, growth, segments, channels) | Stream 3 | 5–7 page brief + key charts |
| Competitive positioning map (8–10 brands, price / origin / channel / consumer) | Stream 3 + Stream 4 | 1-page visual map + commentary |
| Trade channel map & gatekeeping insights (retailer / distributor / broker dynamics) | Stream 1 | 3–4 page synthesis + channel recommendation |
| Consumer perception of Orfeu in the US (taste, brand attributes, origin story, price point) | Stream 2 | Key insights deck (10–12 slides) + verbatim quotes (On hold) |
| Florida beachhead hypothesis (why FL, which segments, which channel entry point) | Streams 1 + 2 + 3 | 3–4 page strategic narrative |
| Specialty coffee brand case library (8 cases, lessons for Orfeu) | Stream 4 | 8 × 2-page summaries + master comparison table |
| Strategic implications & entry scenarios (3 scenarios: conservative / base / aggressive) | All streams | Board presentation (15–20 slides) |

────────────────────────────────────────────────────────────────────────────────

Strategist Agent (PKA v1 / Alquemia) · Jun 2026 · Reference: H&M Proposal May 20 2026 · Orfeu US Market Entry